## README
LawLearn — Integration & Content Contract | Version 1.0 ¦ 27 October 2026
Purpose | Shared working contract to keep Flutter, backend, Admin Portal, and Content Management Portal aligned.
System rule | Backend API is the only write path. Both portals use the same content domain and question lifecycle. Flutter consumes published content and server-authoritative scoring.
API baseline | REST /v1; JSON; ISO-8601 UTC timestamps; stable IDs; OpenAPI as source of truth. Endpoint names are illustrative until API review.
Content rule | A question is learner-visible only when published, not retired, and valid for the requested jurisdiction/time. Draft/imported content is never automatically published.
Scoring rule | Backend owns answer keys, score calculation, attempt status, timestamps and result. Client must not calculate canonical score/token.
Version rule | Published question versions are immutable. A correction creates a new version. Attempts retain the question_version_id they saw.
Workflow | Draft → In Review → Changes Requested / Approved → Published → Superseded or Retired. Exact transitions are server-enforced.
Suggested stack | Flutter; modular-monolith API (FastAPI or NestJS); PostgreSQL; object storage; background worker; OpenAPI; CI/CD. Pick one backend framework during discovery.
How to use | Use the sheets as the shared working agreement. Update version and change log when the team changes a field, endpoint, state or acceptance rule.

## Roadmap
Phase ID | Phase | Timing (estimate) | Primary goal | Flutter | Backend | Admin Portal | Content Portal / Ops | Exit gate | Build status (29 Oct 2026) | What exists today
P0 | Discovery & foundations | W1–2 | Align scope, architecture, legal content policy | User flows; design system | Architecture; OpenAPI skeleton; data model | Admin workflows/roles | Taxonomy; source policy; reviewer workflow | Scope, owner, API conventions and content policy approved | Partly done | Design system (Terracotta x Sand) and learner flows exist. Backend stack chosen (NestJS + Postgres), OpenAPI contract in backend/openapi.json. Still needed: PRD sign-off, source policy, data dictionary.
P1 | Platform foundation | W3–5 | Working environments and access | App shell; auth integration | Auth/RBAC; migrations; logs; CI/CD | Portal shell; roles | Portal shell; draft workspace | All clients authenticate against staging | Mostly done | Learner and staff sign-in with roles, database migrations, CI on every push (backend, portal, app), a staging server with HTTPS and nightly database backups, standard API errors, and the app and portal shells. Still missing: staff management pages, analytics and crash reporting.
P2 | Content pipeline | W4–7 | Publish reviewed questions safely | Consume published topics (integration) | Content lifecycle/source APIs; import jobs | Operations and import visibility | Author/review/approve/publish; audit | Reviewed sample pack appears in app | Mostly done | Content Management Portal: write, review and publish questions with fixed versions and an audit log; bulk submit / approve / publish; CSV / Excel import (drafts only, with a test run and row-level errors) and export; a Topics page for subjects, topics and acts; and Staff accounts with one-time setup links and role changes. The 108 starter questions carry researched sources, official links and validity dates. Still missing: a real legal reviewer signing off a sample pack on staging (the exit gate).
P3 | Learner MVP | W6–9 | Deliver end-to-end learning loop | Topics; quiz; results; bookmarks; mistakes | Quiz session; server scoring; progress APIs | Reports and support views | Maintain launch content pack | Scoring and content parity tests pass | Mostly done | Quizzes run on the server: it picks the questions, keeps the answer keys and scores (including exam minus marks). Results, XP, stars, streak, coins, energy and settings are saved to the account. Saved questions, mistake review and report-a-question are built, and each explanation links to its official source. Still missing: QA sign-off of the learner journey on staging.
P4 | Beta hardening | W10–11 | Quality, security, accessibility and analytics | Crash reporting; accessibility | Monitoring; performance; security | Operational dashboard | Content audit; correction queue | UAT and release checklist signed | Partly done | Started. Done: premium hidden for the beta (the app and the API), in-app account deletion, crash reporting in the app with Sentry (errors only, no personal details), and a corrected privacy text. Decided: our own usage events for analytics, citizens as the beta audience, production hosting later. Still to do: Sentry for the API and the portal, usage events and a dashboard, minimum app version, translations of English-only screens, accessibility and dark-mode check, shared sign-in rate limit, key rotation, store preparation. Automated tests: 65 unit and 97 API tests for the backend, 44 for the app.
P5 | Controlled launch | W12 | Release to limited cohort | Store/release build | Production deploy and rollback | Support/admin operations | Content support rota | Launch owner accepts telemetry and support plan | Not started | Nothing yet. A staging server is running for testing (staging-api / staging-cms.deepwebstudio.dev).
P6 | Retention | Post-launch | Improve repeat learning | Daily challenge; reminders; spaced repetition | Scheduled jobs; recommendations | Engagement analytics | New reviewed topic packs | Feature tied to measured learner need | Partly done | Ahead of plan: streaks with freezes, Daily Docket, exam modes and real weekly leagues (on the server, topped up with practice players), 6 app languages. Still missing: push reminders, spaced repetition, language packs for quiz content.
P7 | Advanced | Discovery-gated | AI, institutions, premium | Assistant UI if approved | Grounded AI/citations; evaluation | Institution and billing ops if approved | AI review and content governance | Quality, privacy, cost and legal thresholds met | Prototype only | Ask AI answers through the server with Azure OpenAI (gpt-5.4-mini), 5 free a day; no key in the app. Demo premium only (no real payments). Still missing: answers grounded in approved sources with citations.

## Module Register
Module ID | Module | Primary owners | Phase | Learner app scope | Backend/API scope | Admin Portal scope | Content Portal/Ops scope | Key acceptance criteria | Build status (29 Oct 2026) | What exists today
M01 | Identity & access | Backend, Flutter, Admin, CMP | P1 | Sign-in, session and profile | Auth, refresh, /me, RBAC | User/role administration | Editor/reviewer/publisher access | Server-side permissions; session expiry handled | Done | Email and password sign-in for learners and staff, short-lived access tokens with rotating refresh tokens (reuse detected), roles checked on every request, sign-in rate limit per client. Accounts carry XP, coins and settings across phones. Staff accounts are managed by admins with one-time setup links. Learners can delete their own account in the app, confirmed with their password: their data is removed and nothing links the deleted account to a person.
M02 | Taxonomy & discovery | Backend, Flutter, CMP | P2/P3 | Browse topics, search and filters | Taxonomy and published content APIs | Taxonomy operations | Maintain subjects, acts, topics and tags | Only eligible published content is discoverable | Mostly done | Subjects, topics and acts in the database, served by GET /v1/taxonomy and the quiz catalog; the app maps its 6 chapters to subjects. Content Management Portal → Topics: add, rename, reorder, show or hide subjects (admins), topics and acts (editors and admins), with question counts; slugs are fixed, topics stay in their subject, new subjects start hidden, and hidden topics keep their questions but leave quizzes. Still missing: learner search and filters in the app, and new subjects in the app (it has its 6 chapters built in).
M03 | Question lifecycle | CMP, Backend, Legal Review | P2 | No draft access | State machine and immutable versions | Audit visibility | Draft, submit, review, approve, publish, retire | Cannot publish incomplete or unreviewed content | Done | Content Management Portal: create and edit drafts, submit, request changes, approve (reviewer cannot be the author or an editor), publish, revise, retire. Published versions are fixed; every step is in the audit log. 108 starter questions imported.
M04 | Sources & legal versioning | CMP, Backend | P2 | Show source and relevant provision | Store source/effective/verified metadata | Content quality reports | Verify sources, record review and amendment notes | Every live question has traceable source and review metadata | Partly done | Questions have source title and URL, citation, provision reference and valid-from / valid-to dates, and only questions in force today reach learners. The app shows the source under each explanation with a link to the official text. All 108 starter questions now carry a researched source (official Gazette, India Code, Legislative Department, PIB or Supreme Court links for 105 of them) and the date each answer became correct; the seed puts them into draft revisions for review. Still missing: legal review of those drafts (on staging the questions were first published unreviewed). Two DPDP Act questions only become valid on 13 May 2027, when those sections come into force.
M05 | Quiz catalog | Flutter, Backend, CMP | P3 | Choose quiz and difficulty | Select eligible questions and create session | Configure allowed quiz settings | Tag content to quiz/topic | Session contains only eligible published versions | Done | GET /v1/quizzes lists topics with published questions in force; four modes (Case Path, Daily Docket, Duel, Exam Chamber) with question counts, difficulty and the daily set chosen by the server.
M06 | Quiz session & scoring | Flutter, Backend, QA | P3 | Answer, submit, view result | Session state, answer validation and scoring | Operational troubleshooting | Ensure answer key and explanation quality | Server-authoritative, idempotent scoring; no key leakage | Done | The server starts the quiz, picks and shuffles the questions, keeps the answer keys, times each answer and scores it, including exam minus marks (+1 / −0.25). Answers are explained after they are final (practice) or after submit (exam). No answer keys in the app.
M07 | Results & progress | Flutter, Backend | P3 | History and progress UI | Attempts, result and aggregation APIs | Analytics view | Review topic-level content quality | Progress survives restart/device change after sync | Done | Results with server-worked stars, XP, streak and coins; GET /v1/me/progress and attempt history; progress follows the account to any phone. Real weekly leagues with promotion and demotion.
M08 | Bookmarks & mistakes | Flutter, Backend | P3 | Save/revisit questions | Bookmark and mistake APIs | Support lookup | Handle retired/superseded content | Bookmarks sync; attempts retain historical question version | Done | Learners save questions (kept on the account) and see a mistakes list: questions whose latest final answer was wrong, which leave the list when answered right later. Mistake practice is free and earns XP. Review card on Home and a Review page (Mistakes / Saved); saved and mistake items show the version the learner answered.
M09 | Import/export | Admin/CMP, Backend/worker | P2 | None | Import job, validation, export | Job status and failure reports | CSV/XLSX preview and row-level correction | Imports create drafts only; row errors are actionable | Done | Content Management Portal → Imports: upload a .csv (UTF-8) or .xlsx file of up to 500 questions, check it first (nothing saved; every row's result with column and reason), then import the valid new rows as drafts only. Unknown columns refuse the file; rows already in the bank (same external_ref, or same text in the same topic) are skipped; repeats inside a file fail; the same file can't be imported twice. Each import keeps a saved report. Export to CSV or Excel in the same columns (follows the status and topic filter), so a file can be edited and imported back.
M10 | Admin operations | Admin, Backend | P1/P2 | None | Admin APIs and RBAC | Users, roles, jobs, reports | Role-specific editor access | Permission matrix and audit tests pass | Mostly done | Roles (admin, editor, reviewer, publisher, analyst, learner) are enforced in the API and the portal, and actions are audit-logged. Content Management Portal → Staff (admins): invite staff with a one-time link to choose their own password, change roles, disable or enable accounts (signs out at once), and issue a new setup link; nobody can remove their own admin role and there is always an active admin. Also in the portal: Topics, Reports, Imports and bulk review actions. Still missing: feature flags and operational settings pages.
M11 | Analytics | All teams | P1/P4 | Versioned client events | Server metrics and aggregates | Dashboards | Content quality and review metrics | Events validated; no secrets or answer keys in telemetry | Not started | No analytics events or crash reporting yet.
M12 | Corrections & moderation | Flutter, Admin, CMP, Backend | P3/P4 | Report a question | Reports, triage status, audit | Queue and resolution tracking | Investigate, correct, retire, republish | Report never directly edits live content | Mostly done | Learners report a question from its explanation or the results review (reason + comment, 20 a day). Staff see and close reports in the portal (Reports page, open reports on each question page, urgent reasons first, audit-logged); a report never changes content. Still missing: telling the reporter the outcome (needs M14).
M13 | Localization/accessibility | Flutter, CMP, Backend | P4+ | Locale, scalable text, screen reader | Localized content support | Review status visibility | Translation and legal review | Safe language fallback; translated legal content reviewed | Partly done | App UI in 6 languages (English, Hindi, Tamil, Telugu, Kannada, Malayalam) with English fallback. Quiz content is English only on the server for now; the newest screens are English only; translated content has no legal review; accessibility not audited.
M14 | Engagement | Flutter, Backend, Admin | P6 | Streaks, reminders, daily challenge | Preferences, scheduler, push tokens | Engagement metrics | Publish scheduled challenge packs | Opt-out respected; jobs timezone-aware and deduplicated | Partly done | Streaks with freezes and milestones, Daily Docket, energy, coins and real weekly leagues all run on the server. Still missing: push reminders, notification preferences, scheduled jobs.
M15 | AI assistance | Flutter, Backend, Legal Review | P7 | Ask for explanation | Grounded retrieval, citations, evaluations | Quality/usage oversight | Curated corpus and human review | Citations/fallback work; no direct AI-to-publish | Prototype only | Ask AI answers through POST /v1/chat on the server with Azure OpenAI (gpt-5.4-mini), 5 answers a day free; the key stays on the server. Still missing: answers grounded in approved sources, citations, an evaluation set, and legal review of AI answers.

## API Contract
Domain | Method | Illustrative endpoint | Used by | Purpose | Authority / validation | Phase
Auth | POST | /v1/auth/session | Flutter/Admin/CMP | Create session | Auth provider; rate limit; return standard envelope | P1
Auth | GET | /v1/me | All clients | Current identity and permissions | Server-derived role claims | P1
Taxonomy | GET | /v1/taxonomy | Flutter/CMP | Get subjects/acts/topics | Stable IDs; active state; locale fallback | P2
Topics | GET | /v1/topics/{id}/quizzes | Flutter | List available quizzes | Published/eligible content only | P3
Quiz | POST | /v1/quiz-sessions | Flutter | Start a quiz session | Server selects eligible question versions; do not expose answer keys | P3
Quiz | POST | /v1/quiz-sessions/{id}/answers | Flutter | Save answer | Session ownership; allowed answer values; retry policy | P3
Quiz | POST | /v1/quiz-sessions/{id}/submit | Flutter | Submit attempt and score | Backend scoring; idempotency key; server timestamp | P3
Results | GET | /v1/quiz-sessions/{id}/result | Flutter | Get canonical result and explanations | Verify attempt ownership; preserve question version | P3
Progress | GET | /v1/me/progress | Flutter | Progress summary | User-scoped data; privacy controls | P3
Bookmarks | GET/POST/DELETE | /v1/me/bookmarks | Flutter | Manage saved questions | User-scoped; validate referenced content | P3
Editor | POST/PATCH | /v1/editor/questions | CMP | Create/update draft | RBAC; validation; published versions immutable | P2
Editor | POST | /v1/editor/questions/{id}/submit | CMP | Submit for review | State transition and required fields | P2
Review | POST | /v1/editor/questions/{id}/approve | CMP | Approve reviewed version | Reviewer role; record reviewer and decision | P2
Publish | POST | /v1/editor/questions/{id}/publish | CMP/Admin publisher | Publish approved version | Publisher role; all publication gates pass | P2
Import | POST/GET | /v1/admin/import-jobs | Admin/CMP | Create and inspect import jobs | Draft-only imports; row-level errors; idempotency | P2
Reports | POST | /v1/content-reports | Flutter | Report content issue | Rate limit; no direct content mutation | P3
Admin | GET | /v1/admin/analytics/* | Admin | Operational metrics | Admin role; aggregated/minimized data | P4
Assistant | POST | /v1/assistant/answers | Flutter | Source-grounded learning explanation | Later phase; source citations and fallback required | P7

## Content Schema
Field | Type / example | Required to publish? | Owner / source | Validation rule | Visible to learner? | Notes
question_id | UUID/ULID | Yes | Backend | Stable identity across versions | No | Question identity, not version identity
question_version_id | UUID/ULID | Yes | Backend | New immutable ID for each published revision | Usually no | Attempt stores this ID
jurisdiction | IN | Yes | Content editor | Must match supported jurisdiction | Yes | Can be displayed in content metadata
language | en | Yes | Content editor | Supported locale code | Yes | Translations map to canonical concept/question
subject_id | Stable ID | Yes | Taxonomy | Must exist and be active for new publication | Yes | Do not use display label as foreign key
act_id | Stable ID or null | Where applicable | Content editor | Must reference known act/version | Yes | Constitution/article may use separate source model
topic_id | Stable ID | Yes | Taxonomy/editor | Must exist | Yes | Use one primary topic; optional secondary tags
question_type | single_select | Yes | Content editor | Allowed enum documented in API contract | Yes | Start with single_select for MVP if needed
stem | Question text | Yes | Content editor | Non-empty; plain text or sanitized rich text | Yes | No unsupported legal conclusion in stem
options | Array of option IDs and text | For MCQ | Content editor | Unique IDs; valid count; no empty options | Yes | Do not send correctness flags before submission
correct_option_ids | Array | Yes | Restricted editorial API | Must match available options and scoring policy | No before submission | Never include in public quiz payload
explanation | Plain language explanation | Yes | Content editor/reviewer | Must explain why and cite provision/source | After answer/result | Separate legal text from simplified summary
source_title | Official source/case title | Yes | Content researcher | Non-empty and attributable | Yes | Source hierarchy defined by editorial policy
source_url | HTTPS URL | Where available/required by policy | Content researcher | Validate URL; prefer authoritative source | Yes | Store citation text too, not URL only
provision_reference | e.g. Article/section | Yes where applicable | Content editor | Must map to source accurately | Yes | Use field names that avoid conflating old/new statutes
valid_from | ISO date | Yes by publication policy | Content editor/reviewer | Valid date for content applicability | Optional display | Not the same as published_at
valid_to | ISO date or null | No | Content reviewer | Must be after valid_from if present | Optional display | Supports time-bounded applicability
verified_at | ISO datetime UTC | Yes | Legal reviewer | Must be recent under policy | Yes as last verified | Set on review, not every save
reviewer_id | User ID | Yes | Workflow | Must be authorized reviewer | No | Store decision history too
status | draft/in_review/approved/published/retired | Yes | Backend workflow | Transitions enforced server-side | No | Imported content begins as draft
created_at/updated_at | ISO datetime UTC | Yes | Backend | Server-managed | No | Audit timestamps
change_note | Text | On revision | Editor/reviewer | Required for published-content revision | Optional | Explain legal/editorial change

## Workflow & Roles
Current state | Action | Next state | Role allowed | Required checks | Audit required
Draft | Submit for review | In Review | Content Editor | Required fields; source metadata; answer validation | Yes
In Review | Request changes | Draft / Changes Requested | Legal Reviewer | Decision reason and actionable feedback | Yes
In Review | Approve | Approved | Legal Reviewer | Independent review; answer and source verified | Yes
Approved | Publish | Published | Publisher/Admin with publish permission | All required fields; version immutable; publication date and validity set | Yes
Published | Revise | New Draft Version | Content Editor | Existing published version stays live until replacement approved | Yes
Published | Supersede | Superseded | Publisher/Admin | Replacement version linked and valid | Yes
Published | Retire / unpublish | Retired | Publisher/Admin; emergency permission as defined | Reason; impact check; cache invalidation | Yes
Any import row | Import | Draft | Admin/Content Editor | Schema validation; duplicate check; row-level report | Yes
Content report | Triage | Under Review / Resolved / Rejected | Content Moderator/Admin | Report reason and resolution recorded | Yes

## Analytics Events
Event name | Trigger | Required properties | Owner | Privacy/quality rule
onboarding_completed | Learner completes onboarding | user_id pseudonymous, goal, locale, app_version, timestamp | Flutter | Avoid unnecessary personal attributes
quiz_started | Session successfully created | session_id, quiz_id, topic_id, question_count, difficulty | Flutter + Backend | Backend session-created event is canonical
question_answered | Answer accepted by API | session_id, question_version_id, elapsed_ms, attempt_number | Backend | Do not log selected answer or answer key in general telemetry unless explicitly approved for learning analytics
quiz_submitted | Backend finalizes attempt | session_id, score, total, duration, scoring_version | Backend | Canonical completion event; idempotent
result_viewed | Learner opens result | session_id, source_screen | Flutter | Do not double-count render retries
bookmark_changed | Bookmark added/removed | question_id, action | Backend | No question text in event
content_reported | Learner submits report | report_id, reason_category, question_version_id | Backend | No sensitive free-text in analytics pipeline
content_published | Question version published | question_version_id, reviewer_id, publisher_id, content_batch_id | Backend | Audit event; access restricted
app_error | Unhandled error | error_code, app_version, platform, request_id | Client/backend | Never include tokens, secrets or unnecessary user content

## QA & Release Gates
ID | Test / gate | Applies to | Pass criteria | Owner | Blocks release?
Q01 | Auth and role matrix | Flutter/API/Admin/CMP | Allowed roles succeed; all unauthorized operations return expected 401/403 | QA + Backend | Yes
Q02 | Content publication lifecycle | CMP/API/Flutter | Draft and approved-but-unpublished content never appears in learner API | QA + Content Lead | Yes
Q03 | Source and review metadata | CMP/API | Published questions satisfy required source, reviewer, jurisdiction and date policy | Content QA | Yes
Q04 | Answer-key secrecy | API/Flutter | Public quiz payload does not expose correctness before answer submission | Security + QA | Yes
Q05 | Scoring parity | API/Flutter | Server result matches documented scoring policy for all test fixtures | QA + Backend | Yes
Q06 | Idempotent submission | API/Flutter | Retrying submit does not create duplicate attempts or change finalized score | QA + Backend | Yes
Q07 | Version preservation | API/CMP | Published edit creates a new version; historical attempt still references original version | QA + Backend | Yes
Q08 | Import validation | Admin/CMP/API | Bad rows show row/field/reason; import never auto-publishes | QA + Content Ops | Yes
Q09 | Accessibility and error states | Flutter/Admin/CMP | Keyboard/screen-reader/scalable text and empty/loading/error states covered | QA + Design | Yes
Q10 | Monitoring and rollback | API/clients/ops | Dashboards and alert owner exist; rollback steps rehearsed | Engineering/Ops | Yes
Q11 | Content correction | Flutter/Admin/CMP/API | Report enters queue; reviewer can correct/retire with audit trail | QA + Content Lead | Yes
Q12 | Privacy and security review | All | No secrets in logs; least privilege; data retention and deletion documented | Security/Privacy owner | Yes

## Change Log
Version | Date | Change | Owner | Approval
1.0 | 2026-10-27 | Initial baseline: roadmap, module register, illustrative API contract, content schema, workflow, analytics and QA gates. | Product Manager | Pending team review
1.0.1 | 2026-10-27 | Added build-status columns (Module Register, Roadmap) for the current offline Nyaya Flutter app. Built but not in this plan: a Legal Updates feed (10 curated landmark judgments and laws, with save) and a demo premium paywall. Payments are out of scope for the first release. | Engineering | Pending team review
1.0.2 | 2026-10-29 | Updated build status (Roadmap, Module Register) to 29 Oct 2026: NestJS backend, Content Management Portal, staging server, server-side quizzes, scoring, progress, economy and weekly leagues, and Ask AI through the server. | Engineering | Pending team review
1.0.3 | 2026-10-29 | Updated build status: researched sources and validity dates on the 108 starter questions (M04), source links in the app, saved questions and mistake review (M08), report-a-question (M12); P3 mostly done. | Engineering | Pending team review
1.0.4 | 2026-10-29 | Updated build status: question import / export (M09 done), bulk submit / approve / publish in the portal; P2 still needs taxonomy and staff pages and a reviewed sample pack. | Engineering | Pending team review
1.0.5 | 2026-10-29 | Updated build status: Topics page for subjects, topics and acts (M02 mostly done, M10 partly done); P2 still needs staff account pages and a reviewed sample pack. | Engineering | Pending team review
1.0.6 | 2026-10-30 | Updated build status: staff accounts with one-time setup links and role changes (M10 mostly done); P2 mostly done, waiting for a reviewed sample pack. | Engineering | Pending team review
1.0.7 | 2026-10-30 | Updated build status: P4 started (premium hidden for the beta; learners can delete their own account in the app); M01 done. | Engineering | Pending team review
1.0.8 | 2026-10-30 | Updated build status: crash reporting (Sentry) in the app, corrected privacy text; P4 partly done. | Engineering | Pending team review